## Summary-GroupIterationProgress
This report consists of multiple sheets: 1. the group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 2. the project ontribution sheet to be filled by everyone at the end of the semester, 3. the AI Usage Log to be filled by everyone whenever using AI tools 4. the weekly report sheet, one per teamember member, to be filled in each week. | [14 empty] | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Any other metrics defined in your SPPP
0 | 9/1 - 9/9 | Held first team meeting, assigned team leadership roles, settled on project concept, completed SPPP + risk management doc, completed iteration 0 presentation | None | confusion regarding group size/membership status, confusion regarding iteration 0 deliverables | Plan to improve communication with course leadership regarding assignment deliverables in advance | 0 | 0 | 0 | 0 | 0 | 30 | NA | 5 | 1.5 | 0 | 0 | 0 | 0 | 15 | 5 | 3.5 | N/A
1 | 9/9 - 9/21 | - Managed the loss of two team members. - Created a comprehensive implementation plan and architecture contract for all members. - Implemented user auth, deck creation, editing, and deletion, and card creation, editing, and deletion. - Used good collaboration workflows and, overall, stayed in touch very well as a team to put together a good first iteration of the app. | Overcoming speed bumps of going from zero code to a working app, missing architecture specs, overlapping pull requests, and error scheme within our API, all handled efficiently and without major delay to the project | Loss of two team members representing one-third of our group, forcing us to reassign roles, consider cutting scope, and collaborate more closely as a team to complete the iteration | For iteration 2, we will have more integrated and automated QA from the start in our GitHub workflow, which will help us maintain coding standards with fewer hiccups from here on out. | N/A - not tracked for this iteration. Required work was re-scoped on the spot in team meeting after drops, and executed without new Scrum workflow setup | 0 | 5 | 5 | 0 | 89 | 81.5 | 7.5 | 8.5 | 5 | 9.5 | 19 | 5 | 9.5 | 16 | 9
2 | 9/22-10/5 | - Implemented the following user stories: - Know how many cards are waiting in each deck. - Start studying from my decks and see what's due. - See how my session went and when to come back. - Study a deck in the browser, one card at a time. - Preview when each rating would bring a card back. - See each rating's next review on its button. - See one consistent look on every page. - Study only the cards that are due. - Schedule each card's next review from my rating. - Study a deck, one card at a time. - Save my rating after each card. | Prevented technical issues by doing thorough team-wide planning and scoping before starting any implementation work. Main technical issues were tests breaking, requiring bug fix PRs to merge before any other work could be done. | Inability to find a synchronous meeting time due to varying group members' schedules across work and school obligations | Due to difficulty planning meetings, we laid out plans each week in Discord, reviewed them by PR, and committed them to our repo so everyone could reference them from their development environment while staying in touch via Discord | 36 | 0 | 14 | 14 | 8 | 79 | 76 | 3 | 3.5 | 4.5 | 2 | 18 | 14 | 21 | 11 | 2
3 | 10/6-10/13 | Implemented the following user stories: - Generate cards from a prompt. - Generate cards from a file. - Suggest more cards for my deck. - Accept or reject each suggested card. - Know when a card was written by AI. - Check my typed answer. - Switch between flashcards and typed answers. - Use Cadence from a web address. Other progress: - Put Cadence live on Render's free tier, with every green merge to main deploying automatically. - Built the shared foundations first, so the other tasks could start in parallel the next day. - Gave every task a written contract and acceptance examples, and wrote tests from those examples. - Acted on our Iteration 2 feedback: removed duplicated code, added the missing AI-usage comments, and cleaned up the Jira board. | Render's free tier had limits we only found by deploying: no step to update the database before starting, no private network between services, a start command broken by its quotes, and a database created in a different region from the services. Each was fixed in a small PR. Gemini's free tier allows only 20 requests a day per model and its newest model timed out, so we capped generation at 10 per user and 18 site-wide and chose Gemini 3.5 Flash. Squash merges left main and develop with different histories, so release PRs now use merge commits. CI hit Docker Hub's download limit once and needed a re-run. Review caught a security-scanner alert and a badge layout bug before merge, and demo prep on the live site caught an invisible Reject button. | This was a one-week iteration, with code freeze on Sunday and documentation on Monday. Some work arrived right at the code freeze, which pushed reviews and fixes into the final day. Schedules again left room for only one hour of group meetings. | We assigned the shared foundations to one person first, so everyone else could branch from them the next day, and froze the contracts between tasks so parallel work fit together. Reviewers checked each PR against the plan's acceptance examples and verified claims directly, with race tests on PostgreSQL, browser walkthroughs and Docker tests. We deployed the code before finishing the docs. Since this was the final iteration, the lessons we would carry forward are to deploy to the real host early rather than at the end, and to open draft PRs early so the team can see progress. | 32 | 0 | 12 | 12 | 2 | 77.5 | 74 | 3.5 | 3.5 | 1.5 | 4.5 | 29 | 11 | 3 | 2.5 | 5 | 391 backend tests (98% coverage) and 318 frontend tests (95%), all passing in CI

## AIUsageLog
This sheet records all AI usage by your team members
Who | When | Tools | Tasks & Artifact | Final Use (Accepted / Modified / Rejected) | Evaluation/Modification | Link /Appendix/ Prompt history + output summary
Miles | Week 1 | Claude | SPPP - Overview | Modified | Reviewed AI draft, heavily rewrote/edited, used AI for final proofread | Transcript Appendix
Miles | Week 1 | Claude | SPPP - Related Work | Modified | Reviewed AI brainstorming and research, completed manual follow up research, manually drafted writing structure, used AI to polish and fill gaps | Transcript Appendix
Miles | Week 1 | Claude | repo Readme.md | Accepted | Used completed work (SPPP Overview) to prompt AI to create Readme file, reviewed content in output, and approved | Transcript Appendix
Miles | Week 1 | Claude | SPPP - Glossary | Accepted | Prompted the AI with the body of the SPPP and asked it to create a glossary of abbreviations and terms. Reviewed and accepted the output | Transcript Appendix
Miles | Week 1 | Claude | SPPP - References | Accepted | Prompted the AI with the body of the SPPP and asked it to create a reference section. Reviewed and accepted the output | Transcript Appendix
Paul | Week 1 | Zoom AI | Meeting Minutes | Modified | Reviewed generated content for errors, converted output to bullet points. | Transcript Appendix
Paul | Week 1 | ChatGPT | SPPP - Management Plan | Modified | I evaluated AI-generated output against the instructor’s guidance, project requirements, team constraints, and my own judgment, modifying or rejecting recommendations when they did not align with the project. | Transcript Appendix
Paul | Week 1 | ChatGPT | Presentation | Modified | I evaluated the AI-generated content against our SPPP, project priorities, and presentation time limit, then revised the scope, technical framing, project differentiation, slide content, and script to produce the final presentation. | Transcript Appendix
Nurzat | Week 1 | ChatGPT | Git/GitHub - Lab 1 | Modified | Used AI for troubleshooting problems. Completed the steps manually after evaluating suggested solutions | Transcript Appendix
Nurzat | Week 1 | ChatGPT | SPPP - High-Level Requirements | Modified | Used AI to help organize and refine requirements. Modified the suggestions before incorporating those into the document | Transcript Appendix
Miles | Weeks 2/3 - Iteration 1 | Zoom AI | Meeting Minutes | Modified | Zoom transcript was too verbose and not tailored to the meeting minutes style. I synthesized before accepting. | https://docs.google.com/document/d/11_x_p6k74uiVeYNfny64OmLF-GCFYZDtBJwru9g1PG4/edit?usp=sharing
Miles | Weeks 2/3 - Iteration 1 | Claude | Meeting Minutes | Modified | I used Claude to synthesize the meeting minutes into a style more appropriate, but then I noticed some things that I wanted to emphasize more in particular, so I edited the output. | https://docs.google.com/document/d/11_x_p6k74uiVeYNfny64OmLF-GCFYZDtBJwru9g1PG4/edit?usp=sharing
Miles | Weeks 2/3 - Iteration 1 | Claude | Iteration 1 Implementation Plan | Accepted | I used our SPPP document in plain English, which laid out our full plans in detail, and used Claude to create a technical implementation plan that could be shared with the whole team. I read through, and it was very technically sound, per my experience. I submitted this as a PR for the team to review without modification. | https://docs.google.com/document/d/11_x_p6k74uiVeYNfny64OmLF-GCFYZDtBJwru9g1PG4/edit?usp=sharing
Miles | Weeks 2/3 - Iteration 1 | Claude | WS0 - Structural Setup | Accepted | I asked Claude to use the implementation 1 plan to draft workstream 0. I posted the result as a PR without modification, knowing Myself and my teammates would review it as part of the PR process. | https://docs.google.com/document/d/11_x_p6k74uiVeYNfny64OmLF-GCFYZDtBJwru9g1PG4/edit?usp=sharing
Miles | Weeks 2/3 - Iteration 1 | Claude | WS1 - Backend User Auth | Accepted | I asked Claude to use the implementation 1 plan to draft workstream 1. I posted the result as a PR without modification, knowing Myself and my teammates would review it as part of the PR process. | https://docs.google.com/document/d/11_x_p6k74uiVeYNfny64OmLF-GCFYZDtBJwru9g1PG4/edit?usp=sharing
Miles | Weeks 2/3 - Iteration 1 | Claude | PR Reviews | Modified | Claude provided briefings on all PRs, with levels of risk for accepting each included. I then decided whether to accept or provide feedback across all PRs. | https://docs.google.com/document/d/11_x_p6k74uiVeYNfny64OmLF-GCFYZDtBJwru9g1PG4/edit?usp=sharing
Miles | Weeks 2/3 - Iteration 1 | Claude | Project Documentation | Modified/Accepted | I used the state of our development after the weekend, prior course feedback, and our prior docs to have Claude give suggested edits across all documents. Some were accepted due to good understanding and outputs after my review. Some missed the mark or were too verbose, and I edited. | https://docs.google.com/document/d/11_x_p6k74uiVeYNfny64OmLF-GCFYZDtBJwru9g1PG4/edit?usp=sharing
Osasenaga | Weeks 2/3 - Iteration 1 | Claude | WS2 - Deck and card endpoints | Modified | Used AI to draft the deck and card endpoints. Reviewed the code, ran the tests, and fixed the issues found by CodeQL and my reviewer before merging. | https://docs.google.com/document/d/1yDKeSeU_utQMR-jJxTu9EKa5MkcHAvLkDno3RpmytAU/edit?usp=sharing
Osasenaga | Weeks 2/3 - Iteration 1 | Claude | WS2 - Endpoint tests | Modified | Used AI to draft 36 tests. A reviewer found two weak assertions, so I fixed both and ran the full suite (94 passing) | https://docs.google.com/document/d/1yDKeSeU_utQMR-jJxTu9EKa5MkcHAvLkDno3RpmytAU/edit?usp=sharing
Osasenaga | Weeks 2/3 - Iteration 1 | Claude | PR #17 - git and review fixes | Modified | Used AI to guide me through git, the pull request, and responding to review comments. I checked each step myself before pushing. | https://docs.google.com/document/d/1yDKeSeU_utQMR-jJxTu9EKa5MkcHAvLkDno3RpmytAU/edit?usp=sharing
Duc Anh Nguyen | Week 1 | ChatGPT | Research - similar products (Anki, etc.) | Modified | Used AI output as a starting list, verified products myself and kept only what fit our SRS + AI concept | https://docs.google.com/document/d/1dXd59FPoNi5_5Rw23z4ZPLVWJuVw6bYLHAKzieFopy4/edit
Duc Anh Nguyen | Week 1 | ChatGPT | SPPP - Configuration Management / Infra plan | Modified | Compared CI/CD tools (Jenkins, ArgoCD, GitHub Actions) with AI, made the final choice (GitHub Actions) and wrote the section myself | https://docs.google.com/document/d/1dXd59FPoNi5_5Rw23z4ZPLVWJuVw6bYLHAKzieFopy4/edit
Duc Anh Nguyen | Week 1 | ChatGPT | SPPP - High-Level Requirements brainstorming | Modified | Brought AI suggestions to the team meeting as input; final requirements decided as a team | https://docs.google.com/document/d/1dXd59FPoNi5_5Rw23z4ZPLVWJuVw6bYLHAKzieFopy4/edit
Duc Anh Nguyen | Weeks 2/3 - Iteration 1 | Claude Code | PR Reviews (Iteration 1 branch, PRs #14, #16, #17, #18) | Modified | Claude listed findings with file:line refs; I verified each and posted only the ones I agreed with as PR comments | https://docs.google.com/document/d/1dXd59FPoNi5_5Rw23z4ZPLVWJuVw6bYLHAKzieFopy4/edit
Duc Anh Nguyen | Weeks 2/3 - Iteration 1 | Claude Code | WS3 - Frontend auth (PR #14) | Modified | Built on WS1 backend; split frontend and CI into separate PRs; had Claude remove early extra files and resolve the conflict with PR #16 minimally | https://docs.google.com/document/d/1dXd59FPoNi5_5Rw23z4ZPLVWJuVw6bYLHAKzieFopy4/edit
Duc Anh Nguyen | Weeks 2/3 - Iteration 1 | Claude Code | CI (PR #13) and CodeQL code scanning (PR #15) | Modified | Reviewed workflows, confirmed via GitHub Actions runs; bumped CodeQL v3 to v4 after a PR comment flagged the deprecation | https://docs.google.com/document/d/1dXd59FPoNi5_5Rw23z4ZPLVWJuVw6bYLHAKzieFopy4/edit
Duc Anh Nguyen | Weeks 2/3 - Iteration 1 | Claude Code | CI/CD pipeline + CD to Render (PR #18) | Modified | Rejected a 3-platform deploy for Render only; removed duplicate test workflow; reverted a prebuild commit; rejected a Terraform narrative doc; fixed react-hooks lint by deriving loading state | https://docs.google.com/document/d/1dXd59FPoNi5_5Rw23z4ZPLVWJuVw6bYLHAKzieFopy4/edit
Duc Anh Nguyen | Weeks 2/3 - Iteration 1 | Claude Code | Security + Dependabot cleanup (PR #30) | Modified | Triaged bot PRs, turned off version-update PRs, kept security alerts; rejected first FLASK_DEBUG fix and had Flask read it from env; closed duplicate PR #19 | https://docs.google.com/document/d/1dXd59FPoNi5_5Rw23z4ZPLVWJuVw6bYLHAKzieFopy4/edit
Duc Anh Nguyen | Weeks 2/3 - Iteration 1 | Claude Code | SDD (architecture) and STD - all sections | Modified | Claude drafted from SPPP and Team Docs; I corrected details (e.g. Render as deploy target) and pasted the final text myself | https://docs.google.com/document/d/1dXd59FPoNi5_5Rw23z4ZPLVWJuVw6bYLHAKzieFopy4/edit
Duc Anh Nguyen | Weeks 2/3 - Iteration 1 | Claude Code | Progress report entry + AI Usage appendix | Modified | Claude drafted from my notes, commits and session history; I reviewed for accuracy before submitting | https://docs.google.com/document/d/1dXd59FPoNi5_5Rw23z4ZPLVWJuVw6bYLHAKzieFopy4/edit
Nurzat Mukhamedali | Week 2 | ChatGPT | Quiz 1 preparation and Lab 2 assistance | Modified | Used explanations to review course concepts and work through lab tasks. | AI explained course topics and assisted with Lab 2.
Nurzat Mukhamedali | Week 3 – Iteration 1 | Codex | WS4 deck and card frontend, PR #16 | Modified | Tried the interface and requested changes to empty states, first-card creation, and Finish/Cancel behavior. Refined the implementation through teammate feedback. | PR #16. AI assisted with implementation, explanations, testing, and interface revisions.
Nurzat Mukhamedali | Week 3 – Iteration 1 | Codex | Integration conflicts and expired-session fix | Modified | Used AI to investigate review feedback and implement fixes. Checked the updated behavior and pushed changes for teammate review. | PR #16. AI assisted with authentication/routing integration, conflict resolution, and expired-session handling.
Nurzat Mukhamedali | Week 3 – Iteration 1 | Codex | Teammate pull request reviews | Modified | Used AI explanations and review findings to help understand proposed changes and prepare review feedback. | PR #14 and PR #30. AI examined changes and explained findings and the GitHub review process.
Nurzat Mukhamedali | Week 3 – Iteration 1 | Codex | Iteration 1 presentation and narration | Modified | Adapted AI-generated material to the group’s work. Requested shorter scripts for assigned slides and an ending appropriate for a recording. | AI helped with the plan of the slides and narration. Final assigned slides: 2, 4, 7, and 10.
Miles Cameron | Week 4 - Lab 3 | Claude Code | Jira user story board | Accepted | Based on team documentation, the state of our codebase, an example of a previous well-formatted user story, and the intent of Lab 3, Claude drafted well-scoped user stories to base the lab on for our team and input them to Jira using the Jira CLI. I reviewed the stories it wrote, and all followed the input examples and content well, and were accepted
Duc Anh Nguyen | Weeks 4/5 - Iteration 2 | Claude Code | Lab 3 Story 3 - study session reducer (PR #40) | Modified | Claude wrote the tests first as a red commit, then the reducer; I checked every Given/When/Then row in the plan had a test before opening the PR | https://docs.google.com/document/d/1Z174UgnBDEYbMke_WBkgr4RyKOvycMlz-DH28yrg700/edit
Duc Anh Nguyen | Weeks 4/5 - Iteration 2 | Claude Code | PR Reviews (PRs #33-#39, #41-#48, #54) | Modified | Claude listed findings; I verified each before posting: recomputed scheduler arithmetic by hand and asked for the missing red commit (#39), deck ids changing after seed --reset (#47), rebase fix for stale squash commits (#48) | https://docs.google.com/document/d/1Z174UgnBDEYbMke_WBkgr4RyKOvycMlz-DH28yrg700/edit
Duc Anh Nguyen | Weeks 4/5 - Iteration 2 | Claude Code | F3 - session summary (PR #49) and F1 - study page (PR #51) | Modified | Claude implemented both from the plan's acceptance examples with one test per example; I reviewed them against the plan and the props other chunks depended on | https://docs.google.com/document/d/1Z174UgnBDEYbMke_WBkgr4RyKOvycMlz-DH28yrg700/edit
Duc Anh Nguyen | Weeks 4/5 - Iteration 2 | Claude Code | Frontend coverage gate (PR #50) and Iteration 1 frontend tests (PR #52) | Modified | Started the gate at 30% and held study code at 90%; raised it to 90% for the whole frontend once #52 covered the Iteration 1 pages (174 tests, 91.66%) | https://docs.google.com/document/d/1Z174UgnBDEYbMke_WBkgr4RyKOvycMlz-DH28yrg700/edit
Duc Anh Nguyen | Weeks 4/5 - Iteration 2 | Claude Code | SPPP and risk register - Iteration 2 update; submission docs branch | Modified | Claude checked the doc plan against the code and CI and filled CI numbers; I had edits made directly instead of as suggestions and set myself as author; values not in the repo were left out, not guessed | https://docs.google.com/document/d/1Z174UgnBDEYbMke_WBkgr4RyKOvycMlz-DH28yrg700/edit
Duc Anh Nguyen | Weeks 4/5 - Iteration 2 | Claude Code | Progress report entry + AI Usage appendix | Modified | Claude drafted from my PRs, reviews and commit history; I reviewed for accuracy and entered my hours myself | https://docs.google.com/document/d/1Z174UgnBDEYbMke_WBkgr4RyKOvycMlz-DH28yrg700/edit
Osasenaga Okunbor | Weeks 4/5 - Iteration 2 | Claude | B3 - interval previews (PR #53) | Modified | Claude drafted preview_intervals() and Card.to_study_dict() from the plan; I checked every value against the plan's reference table, ran the full suite in Docker (185 passed) and added the AI usage comments to the code | https://docs.google.com/document/d/1yDKeSeU_utQMR-jJxTu9EKa5MkcHAvLkDno3RpmytAU/edit?usp=sharing
Osasenaga Okunbor | Weeks 4/5 - Iteration 2 | Claude | B3 - interval preview tests (PR #53) | Modified | Claude wrote one test per acceptance example; I confirmed they failed before the code and passed after, on SQLite and PostgreSQL; all CI checks passed and Miles approved | https://docs.google.com/document/d/1yDKeSeU_utQMR-jJxTu9EKa5MkcHAvLkDno3RpmytAU/edit?usp=sharing
Osasenaga Okunbor | Weeks 4/5 - Iteration 2 | Claude | Git workflow, PR #53 and progress report entry | Modified | Claude guided me through stashing old changes, branching, applying the patch and opening the PR, and drafted my progress report entry; I checked each step's output and entered my own hours | https://docs.google.com/document/d/1yDKeSeU_utQMR-jJxTu9EKa5MkcHAvLkDno3RpmytAU/edit?usp=sharing
Miles Cameron | Weeks 4/5 - Iteration 2 | Claude Code | Plan for finalizing iteration 2 | Accepted | Read through the plan's breakdown of tasks and decided the scope was appropriate. Sent to the team for review, knowing the full team would read the plan. | https://docs.google.com/document/d/1HrGPLoT1qi3b8z_VE4kRcRZZBXTl8oV1m11jIw7FrHc/edit?usp=sharing
Miles Cameron | Weeks 4/5 - Iteration 2 | Claude Code | Plan step 0: foundation | Accepted | Claude implemented code for step 0. I gave well scoped direction and then read through it. Given that this was purely foundational code and not functional, I felt comfortable submitting this as a PR for the team to review | https://docs.google.com/document/d/1HrGPLoT1qi3b8z_VE4kRcRZZBXTl8oV1m11jIw7FrHc/edit?usp=sharing
Miles Cameron | Weeks 4/5 - Iteration 2 | Claude Code | Plan step B1: demo data | Accepted | Claude implemented demo data for iteration 1. Given that this was not functional code, but rather the seed for our demo, this was easy to accept, as I would find any issues with it later during the demo itself. | https://docs.google.com/document/d/1HrGPLoT1qi3b8z_VE4kRcRZZBXTl8oV1m11jIw7FrHc/edit?usp=sharing
Miles Cameron | Weeks 4/5 - Iteration 2 | Claude Code | Plan step F2 cards and rating buttons | Accepted | Claude implemented step F2 relating to cards and rating buttons. I submitted this as a PR for the team to review, knowing the demo was close to being done and I could review any bugs manually at that point. Claude had also done an excellent job of implementation thus far due to the well-scoped nature of the inputs. | https://docs.google.com/document/d/1HrGPLoT1qi3b8z_VE4kRcRZZBXTl8oV1m11jIw7FrHc/edit?usp=sharing
Miles Cameron | Weeks 4/5 - Iteration 2 | Claude Code | PR Reviews | Modified | I had Claude boil down code changes to give me thorough reports and things to consider as I did a manual review. | https://docs.google.com/document/d/1HrGPLoT1qi3b8z_VE4kRcRZZBXTl8oV1m11jIw7FrHc/edit?usp=sharing
Miles Cameron | Weeks 4/5 - Iteration 2 | Claude Code | Documentation Updates | Modified | Claude reviewed our codebase compared to our past documentation freezes and recommended changes to each document to make our documentation reflect our latest codebase and decisions that I had used Claude for. | https://docs.google.com/document/d/1HrGPLoT1qi3b8z_VE4kRcRZZBXTl8oV1m11jIw7FrHc/edit?usp=sharing
Nurzat Mukhamedali | Week 4 - Lab 3 | OpenAI Codex | Lab 3 Story 2: Due Cards. Assisted with repository and plan inspection, pytest tests in tests/test_due_cards.py, implementation in app/api/decks.py, Docker test execution, and review before committing. | Modified | Helped to complete RED before implementation: 7 tests failed and 4 passed. After implementing due-card selection, all 11 tests passed locally and inside Docker. I captured screenshots of the RED, GREEN, and Docker results. No RED commit was created or reconstructed. | PR #41: https://github.com/BUMETCS673/CS673OLF26P2/pull/41. Prompt summary: Codex helped to inspect Story 2 requirements, write tests, implement the minimum code to pass, verify Docker execution, and review the changes. Output: due-cards endpoint implementation, 11 pytest tests, and reproducible test commands. AI was used to help apply TDD and verify the implementation against the team’s acceptance requirements.
Nurzat Mukhamedali | Week 5 - Iteration 2 | Devin (Cognition AI) | B2 / SCRUM-79: due_counts on every deck API response (backend app/api/decks.py) + tests (tests/test_deck_due_counts.py) | Accepted | Checked the code against the B2 acceptance table in FINALIZE_ITERATION_2_PLAN.md (one test per row). Verified all 201 backend tests pass on SQLite and PostgreSQL, coverage stays above 90%, counts match GET /api/decks/:id/due, and the seeded data gives Spanish 101 {0,0,4} and Travel Spanish {3,3,3}. CI passed and a teammate reviewed it before merge. Chose this version over an unfinished earlier Codex attempt. | PR #55: https://github.com/BUMETCS673/CS673OLF26P2/pull/55. Prompt summary: asked Devin to help with Iteration 2 tasks, then implement B2 with tests. Output: grouped SQL due-count query + test file, delivered as a patch I applied and pushed.
Nurzat Mukhamedali | Week 5 - Iteration 2 | Devin (Cognition AI) | F4 / SCRUM-84: Study buttons, due-count badges, and per-card schedule badges on the deck pages (describeSchedule.js, DeckListPage.jsx, DeckDetailPage.jsx) + Vitest tests | Modified | Checked it against the F4 acceptance table and in the running app. All frontend tests, lint, and build pass. In review, Miles found the badge didn't update after adding or deleting a card. Devin then made the page refresh the deck's due counts after card changes (old counts stay if that request fails), added 3 tests, and made + Add card a secondary button. After the fix, 174 frontend tests pass and CI is green. | PR #56: https://github.com/BUMETCS673/CS673OLF26P2/pull/56. Prompt summary: asked Devin to implement F4 with tests, then asked for help with the reviewer's comment. Output: original F4 commit + a follow-up fix commit, both delivered as patches I applied and pushed.
Osasenaga Okunbor | Week 6 - Iteration 3 | Claude | B4 - accept and reject endpoints (PR #69) | Modified | Chose AI to turn the plan's 10 acceptance examples into tests quickly before code freeze. Confirmed 22 tests failed before the code and all 391 passed after, on SQLite and PostgreSQL. Fixed the CodeQL assert issue Miles flagged in review | https://docs.google.com/document/d/1HrGPLoT1qi3b8z_VE4kRcRZZBXTl8oV1m11jIw7FrHc/edit?usp=sharing
Osasenaga Okunbor | Week 6 - Iteration 3 | Claude | F3 - Generate with AI button and AI badges (PR #70) | Modified | Chose AI because F3 changed four files teammates own and it could follow their patterns. Confirmed 5 new tests failed first, then all 266 frontend tests, lint and build passed. Fixed the badge layout on the study card after Miles's review | https://docs.google.com/document/d/1HrGPLoT1qi3b8z_VE4kRcRZZBXTl8oV1m11jIw7FrHc/edit?usp=sharing
Duc Anh Nguyen | Week 6 - Iteration 3 | Claude Code | B1 prompt builder and cleanup (PR #65), B3 generate endpoint (PR #66), F2 review list (PR #67) | Modified | Claude implemented each step from the plan's acceptance examples with tests; I checked the code against the plan's contracts and CI before opening each PR | https://docs.google.com/document/d/1FBXr9E6gkZhvCBCipLuz644xg90u52oOHfWMe3bUtLU/edit
Duc Anh Nguyen | Week 6 - Iteration 3 | Claude Code | PR Reviews (PRs #59-#62, #64, #74, #76) | Modified | Claude listed findings; I verified each before posting, e.g. a file chosen earlier still sent after switching modes (#62) and the internal API_ORIGIN left in CICD.md (#59) | https://docs.google.com/document/d/1FBXr9E6gkZhvCBCipLuz644xg90u52oOHfWMe3bUtLU/edit
Duc Anh Nguyen | Week 6 - Iteration 3 | Claude Code | P2 Render setup (PRs #63, #68) and doc/CICD.md update | Modified | Claude drafted the start-command migration fix and the CICD.md changes; I had it remove narrative text and guessed values before pushing | https://docs.google.com/document/d/1FBXr9E6gkZhvCBCipLuz644xg90u52oOHfWMe3bUtLU/edit
Duc Anh Nguyen | Week 6 - Iteration 3 | Claude Code | Shared frontend and API helpers refactor (PR #75) | Modified | Claude moved repeated code into shared helpers; I reviewed the diff and confirmed CI passed (391 backend and 318 frontend tests) | https://docs.google.com/document/d/1FBXr9E6gkZhvCBCipLuz644xg90u52oOHfWMe3bUtLU/edit
Duc Anh Nguyen | Week 6 - Iteration 3 | Claude Code | SPPP - Iteration 3 update | Modified | Claude checked the SPPP against the code and CI and edited the Google Doc directly; I set myself as author, and values not known yet (live URL, story acceptance rate, hours) were left out, not guessed | https://docs.google.com/document/d/1FBXr9E6gkZhvCBCipLuz644xg90u52oOHfWMe3bUtLU/edit
Duc Anh Nguyen | Week 6 - Iteration 3 | Claude Code | Progress report entry + AI usage log | Modified | Claude drafted from my PRs, reviews and commit history; I reviewed for accuracy and entered my hours myself | https://docs.google.com/document/d/1FBXr9E6gkZhvCBCipLuz644xg90u52oOHfWMe3bUtLU/edit
Duc Anh Nguyen | Week 6 - Iteration 3 | Claude Code | P2 Render deployment: Blueprint setup, deploy hooks, start command fix (PRs #79, #81), database region fix (PRs #82, #83) | Modified | Claude guided the Render setup step by step and diagnosed both failed deploys from the Render logs (quoted start command, database in another region); I made the dashboard changes, entered the deploy hooks from my clipboard so they never appeared in chat, and confirmed the live site and the CD health check | https://docs.google.com/document/d/1FBXr9E6gkZhvCBCipLuz644xg90u52oOHfWMe3bUtLU/edit
Nurzat Mukhamedali | Week 6 - Iteration 3 | Devin (Cognition AI) | Prepared and organized typed-mode code into PRs: F4 typed-answer checker, F5 typed-mode building blocks, and F6 typed study flow. | Modified | Used Devin’s assistance to prepare the three PRs. All three received teammate approval and passed CI checks. | Devin helped prepare and organize my Iteration 3 typed-mode code into three pull requests: #71 for the F4 typed-answer checker, #72 for the F5 typed-mode building blocks, and #73 for the F6 typed study flow. Together, these contributions covered checking typed answers, supporting typed-mode controls and answer feedback, and integrating typed answers into the study session. F6 depended on F4 and F5. All three pull requests received teammate approval and passed CI checks.
Nurzat Mukhamedali | Week 6 - Iteration 3 | OpenAI Codex | Drafted the Iteration 3 presentation slides and speaker notes using the team’s presentation plan and Iteration 2 deck. | Modified | Helped with a 12-slide presentation matching the previous presentation’s design. | Codex helped to generate a 12-slide Iteration 3 PowerPoint draft using the team’s presentation plan and the Iteration 2 deck as a design reference. The slides covered team roles, delivered features and scope changes, typed-answer behavior, AI-generation architecture, deployment workflow, automated and acceptance testing, review findings, security, lessons learned, and next steps. The deck included speaker notes for each presenter, source references, and an AI-usage disclosure. The output was saved as CS673_presentation3_team2.
Nurzat Mukhamedali | Week 6 - Iteration 3 | OpenAI Codex | Drafted the weekly progress-report entry and AI-usage log. | Modified | Clarified the tools used and final-iteration status. | Codex helped organize my Iteration 3 contributions into the weekly progress-report format. It helped write task descriptions for the completed quiz, typed-mode PRs, presentation preparation, recordings, video assembly, meeting minutes, and reporting activities. It also drafted project-deliverable contributions, coordination issues, follow-up plans, and AI-usage entries describing assistance from Devin and Codex.
Miles Cameron | Week 6 - Iteration 3 | Claude Code | Iteration 3 plan (PR #59) | Modified | I described every feature and cut multiple choice, and had Claude propose the architecture with a non-technical summary before writing any plan. I corrected it where it gave me all the documentation, approved the architecture, then revised the plan after Duc's two reviews. I accepted five of his seven recommendations, such as a site-wide cap of 18 generations a day and a lock against duplicate accepts. | https://docs.google.com/document/d/1PtrT3OP5BBolQgMxvRHv78YWS8qIIAJ_s91v-tsFDoM/edit?usp=sharing
Miles Cameron | Week 6 - Iteration 3 | Claude Code | Step 0a backend foundation (PR #60) and step 0b frontend foundation (PR #61) | Modified | Claude built both steps from the plan's contracts with tests (226 backend, 206 frontend) and stopped before committing. I checked every changed file, made each commit and PR myself, and had it address Duc's review on #60 by switching to the backend's public address. | https://docs.google.com/document/d/1PtrT3OP5BBolQgMxvRHv78YWS8qIIAJ_s91v-tsFDoM/edit?usp=sharing
Miles Cameron | Week 6 - Iteration 3 | Claude Code | P1 - Gemini API key and model choice | Modified | Claude explained where the key belongs (a local .env file and Render's settings, never a commit or the chat), and I entered it myself. My first choice, Gemini 3.8 Flash, timed out in testing, so I rejected it. A diagnostic Claude wrote showed 3.5 Flash's errors came from Google being overloaded, and I chose 3.5 Flash with Flash-Lite as the fallback. | https://docs.google.com/document/d/1PtrT3OP5BBolQgMxvRHv78YWS8qIIAJ_s91v-tsFDoM/edit?usp=sharing
Miles Cameron | Week 6 - Iteration 3 | Claude Code | B2 - Gemini provider and flask ai-smoke (PR #64) | Modified | Claude wrote the provider and its tests (267 passing, 97% coverage), including checks that prompts and replies never reach the logs. I had it add a low thinking setting and a clear learner message for each kind of Gemini failure, and ran the live smoke test with my own key. | https://docs.google.com/document/d/1PtrT3OP5BBolQgMxvRHv78YWS8qIIAJ_s91v-tsFDoM/edit?usp=sharing
Miles Cameron | Week 6 - Iteration 3 | Claude Code | F1 - generate form (PR #62) | Modified | Claude built the three-mode form with 39 tests. Duc's review found that a file chosen earlier was still sent after switching modes, so I had it fixed and re-requested review. | https://docs.google.com/document/d/1PtrT3OP5BBolQgMxvRHv78YWS8qIIAJ_s91v-tsFDoM/edit?usp=sharing
Miles Cameron | Week 6 - Iteration 3 | Claude Code | Refactor from Iteration 2 feedback (PR #74) | Accepted | From our grading feedback, Claude proposed a narrow refactor: one shared deck ownership check instead of three copies, plus the missing AI-usage comments. There was no behavior change and every backend test passed unchanged, so I accepted it after reading the diff. | https://docs.google.com/document/d/1PtrT3OP5BBolQgMxvRHv78YWS8qIIAJ_s91v-tsFDoM/edit?usp=sharing
Miles Cameron | Week 6 - Iteration 3 | Claude Code | PR reviews (PRs #63, #65-#73, #77-#84) | Modified | For each PR I asked for a plain-language summary, a recommendation and draft review text, then decided what to post. Claude verified instead of assuming: it raced 40 simultaneous accepts on PostgreSQL (#69), rendered the study card in a browser (#70), tested nginx with a trailing slash (#63) and walked every typed-answer example in Chrome (#73). I requested changes on #63, #68, #69 and #70. For #71-#73 I let Claude post the approvals, and I merged #73 myself when its safety check blocked the merge. | https://docs.google.com/document/d/1PtrT3OP5BBolQgMxvRHv78YWS8qIIAJ_s91v-tsFDoM/edit?usp=sharing
Miles Cameron | Week 6 - Iteration 3 | Claude Code | Jira user stories and board cleanup | Accepted | Claude drafted the Iteration 3 stories from our plan and the Iteration 2 grading feedback, quoting the real on-screen messages from the code. I chose what to keep, cut or delete, set owners from the plan, and approved the plan before any change. It tested one story first, caught a formatting bug in the Jira tool, and handed the permanent deletions back to me when its safety check blocked them. | https://docs.google.com/document/d/1PtrT3OP5BBolQgMxvRHv78YWS8qIIAJ_s91v-tsFDoM/edit?usp=sharing
Miles Cameron | Week 6 - Iteration 3 | Claude Code | SDD - diagrams and section edits | Modified | I gave Claude the previous four diagrams and asked for targeted changes. It produced five diagrams, including a new card-generation sequence, and a section-by-section edit list. I asked for complete tables instead of lists of changes so I could paste them, and made the edits in the SDD myself. | https://docs.google.com/document/d/1PtrT3OP5BBolQgMxvRHv78YWS8qIIAJ_s91v-tsFDoM/edit?usp=sharing
Miles Cameron | Week 6 - Iteration 3 | Claude Code | Documentation, presentation and code walkthrough plans | Modified | Claude checked every document against the merged code, CI and PR history, and wrote plans for the team's doc updates, the presentation and the code walkthrough. I had it trim the presentation to about 10 minutes, take out a live demo (our demo is its own video), and give each presenter one block. | https://docs.google.com/document/d/1PtrT3OP5BBolQgMxvRHv78YWS8qIIAJ_s91v-tsFDoM/edit?usp=sharing
Miles Cameron | Week 6 - Iteration 3 | Claude Code | Demo video preparation | Accepted | For the demo on the live site, Claude wrote 10 starter Spanish cards and a simple PDF for the file upload. It also found why each suggestion's Reject button was invisible (white text on a white card) and made a one-line fix with a regression test, which I reviewed before committing. | https://docs.google.com/document/d/1PtrT3OP5BBolQgMxvRHv78YWS8qIIAJ_s91v-tsFDoM/edit?usp=sharing
Miles Cameron | Week 6 - Iteration 3 | Claude Code | Progress report entry and AI usage log | Modified | Claude drafted my contribution summary, weekly entry, these AI log rows and the team's Iteration 3 summary from the PR history, my reviews, Jira and my session logs. It also moved the live-site story to Done and fixed a broken heading in Jira. I supplied my hours and checked each entry before submitting. | https://docs.google.com/document/d/1PtrT3OP5BBolQgMxvRHv78YWS8qIIAJ_s91v-tsFDoM/edit?usp=sharing

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Duc Anh Nguyen | 1. Wrote the Configuration Management Plan section (Iteration 0) 2. Revision 3 for Iteration 2: timeline, configuration management, CI/CD, testing tools, QA metrics, AI usage log 3. Revision 4 for Iteration 3: overview, requirement status, AI nonfunctional requirements, risks, timeline, configuration management, deployment, QA plan, references, glossary 4. Updated the risk register for Iteration 2 | 1. Helped define the high-level requirements in Iteration 0 2. Set up the Jira project: stories, subtasks and user story template (Iteration 1) 3. Reviewed the Iteration 3 plan's contracts and acceptance examples before coding (PR #59) | 1. Wrote the system architecture SDD, all sections (Iteration 1) | 1. Wrote the STD, all sections (Iteration 1) | 1. Presented in the Iteration 0 presentation 2. Presented in the Iteration 1 and 2 presentations 3. Iteration 3: design and implementation and deployment block, and a code walkthrough segment | 1. Frontend auth: API client, auth context, route guards, login and signup (WS3, PR #14) 2. Study session reducer (PR #40) 3. Session summary (F3, PR #49) and study page (F1, PR #51) 4. AI prompt builder and output cleanup (B1, PR #65) 5. Generate endpoint with file checks and daily caps (B3, PR #66) 6. Review list for AI suggestions (F2, PR #67) 7. Shared frontend and API helpers refactor (PR #75) | 1. Study session reducer tests written first, one per acceptance example (PR #40) 2. Tests for the Iteration 1 pages, forms, auth and route guards (PR #52) 3. Frontend coverage report and 90% gate in CI (PR #50) 4. Tests for the prompt builder, cleanup, generate endpoint and review list (PRs #65-#67) 5. Checked teammates' test arithmetic and acceptance coverage in review (e.g. the scheduler, PR #39) | 1. Docker and Docker Compose setup (PR #3) 2. CI on GitHub Actions (PR #13), CodeQL scanning (PR #15) 3. Full CI/CD pipeline: lint, PostgreSQL tests, Docker image scan and smoke test, CD to Render (PR #18) 4. Security fixes, security policy and Dependabot setup (PR #30) 5. Render free-tier deployment: public API_ORIGIN (PR #63), migrations in the start command (PR #68), production database 6. Wrote and maintained the CI/CD guide (doc/CICD.md) | 1. Config/DevOps Leader and Design and Implementation Leader 2. Set up the team repository and merged the Iteration 0 commits (PRs #1, #2) 3. Reviewed 38 teammate PRs across all iterations, including the Iteration 2 release (PR #58) 4. Raised issues in review before merge, e.g. deck ids changing after a reseed (PR #47) and a stale file sent after switching modes (PR #62) | AI use (Claude Code, ChatGPT) is recorded in the AIUsageLog and in my AI usage appendices for each iteration.
Nurzat Mukhamedali | 1. Contributed high-level functional and nonfunctional requirements in Iteration 0 as Requirements Leader. 2. Proposed essential, desirable, optional, and nonfunctional requirements to help define the project’s initial scope. 3. Clarified feature requirements across later iterations, including deck/card management, study behavior, and typed answers. My contribution focused on requirements content rather than compiling the full SPPP document. | 1. Defined and clarified high-level project requirements as Requirements Leader. 2. Iteration 1: clarified deck and card workflows, including empty states, first-card creation, and Finish/Cancel behavior. 3. Lab 3: reviewed Story 2 requirements and acceptance criteria for retrieving due cards. 4. Iteration 2: clarified B2 due-count and F4 deck-page requirements, including expected Study-button, due-count, and schedule-badge behavior. 5. Iteration 3: reviewed typed-answer requirements and acceptance criteria for F4, F5, and F6, covering answer checking, typed-mode components, and integration into the study flow. | 1. Iteration 1: refined the layout and interactions for deck and card management, including creation, editing, deletion, input validation, empty states, and cancellation behavior. 2. Iteration 2: translated study requirements into deck-page interactions through Study buttons, due-count indicators, and card schedule badges. 3. Iteration 3: contributed to the frontend behavior of typed-answer checking, answer feedback, study-mode controls, and integration with the existing study session. 4. My design contribution was through feature behavior and implementation rather than authorship of the complete SDD. | 1. Lab 3: documented the due-cards endpoint’s automated test results, including RED and GREEN phases and screenshots of passing tests. 2. Verified that all 11 Lab 3 Story 2 tests passed locally and inside Docker, and captured the required evidence. 3. Recorded feature-testing and CI outcomes in my weekly progress reports for deck/card management, due counts, deck-page study controls, and typed-mode functionality. 4. My documentation contribution focused on testing evidence for my assigned features rather than authorship of the complete STD. | 1. Iteration 1: helped prepare presentation slides and their narration. 2. Iteration 2: created the PowerPoint, prepared and shortened the speaking script, and recorded the presentation. Incorporated Miles’s recorded demo segment. 3. Iteration 3: prepared the presentation slides and speaker notes based on the team’s plan and previous deck. 4. Recorded my Iteration 3 presentation section covering the introduction, team roles, scope, and typed answers. 5. Recorded my code walkthrough section covering deck pages, due cards and counts, typed-answer checking, and the typed study flow. 6. Edited and combined teammates’ presentation recordings into a single presentation video. | 1. Iteration 1: implemented the WS4 deck and card frontend through PR #16, including creation, editing, deletion, input validation, empty states, and improved creation/cancellation flows. 2. Addressed integration conflicts and review feedback, including expired-session handling. 3. Iteration 2 / Lab 3: implemented the due-cards endpoint through PR #41. 4. Iteration 2: added due counts to deck API responses through B2, PR #55. 5. Iteration 2: added Study buttons, due-count badges, and card schedule badges to deck pages through F4, PR #56. 6. Updated due-count refresh behavior after adding or refreshing cards in response to review feedback. 7. Iteration 3: implemented the F4 typed-answer checker through PR #71. 8. Iteration 3: implemented F5 typed-mode building blocks through PR #72. 9. Iteration 3: integrated the F6 typed study flow through PR #73. All three Iteration 3 PRs received approval and passed CI. | 1. Iteration 1: checked deck/card user workflows and regression behavior, including input validation, empty states, creation/cancellation flows, and expired-session handling. 2. Participated in reviewing teammates’ pull requests and checked fixes after integration. 3. Lab 3: completed RED and GREEN testing for the due-cards endpoint, with all 11 Story 2 tests passing locally and inside Docker. 4. Iteration 2: verified automated tests and CI results for due counts and deck-page study controls in PRs #55 and #56. 5. Rechecked due-count refresh behavior after adding or refreshing cards following review feedback. 6. Iteration 3: tested typed-answer functionality and verified passing CI checks for PRs #71, #72, and #73. | 1. Set up and practiced the Git/GitHub development workflow through Lab 1 and Lab 2. 2. Resolved early GitHub merge-conflict and authentication issues. 3. Iteration 1: set up frontend dependencies and resolved branch integration conflicts. 4. Lab 3: used Git branches and Docker CLI commands to run and verify the backend work inside a container. 5. Completed Docker verification through the CLI when the Docker Desktop GUI did not open. 6. My configuration work focused on the local development and testing environment; production deployment was handled by teammates. | 1. Served as Requirements Leader throughout the project, helping clarify scope, feature behavior, and acceptance criteria. 2. Participated in team meetings and coordinated through the team’s shared communication and documentation tools. 3. Coordinated frontend integration, discussed review feedback, and followed up on issues affecting my assigned features. 4. Helped align presentation content with the implemented features and coordinated presentation preparation across iterations. 5. Collected teammates’ Iteration 3 presentation recordings and assembled the combined presentation video. 6. Updated Iteration 3 meeting minutes with meeting details, decisions, and action items. 7. Maintained my weekly progress reports and AI-usage entries. | Used ChatGPT and OpenAI Codex to support learning, requirements clarification, implementation/testing assistance, troubleshooting, presentation preparation, and progress-report drafting. Used Devin to assist with Iteration 2 B2/F4 work and to prepare and organize Iteration 3 typed-mode code into PRs #71–73. AI assistance is documented in the team’s AI Usage Log and my weekly reports. My main technical contributions were deck/card management, due-card retrieval and counts, deck-page study controls, and typed-answer study functionality.
Miles Cameron | 1. Wrote the Overview and Related Work sections, the glossary and the references (Iteration 0) 2. Wrote the repo README from the SPPP overview (Iteration 0) 3. Iteration 1: reviewed and edited every document due, including the SPPP, and committed them for submission 4. Iteration 2: checked the SPPP, risk register, SDD and STD against the shipped code and the Iteration 1 feedback, and wrote the replacement text their owners applied 5. Iteration 3: wrote the documentation plan that directed each teammate's updates (SPPP, risk register, STD, CI/CD guide), with one set of shared numbers for every document | 1. Turned our requirements into each iteration's plan, with tasks, owners, contracts between tasks and Given/When/Then acceptance examples: Iteration 1 (PR #6), Lab 3 (PR #34), Finalize Iteration 2 (PR #43) and Iteration 3 (PR #59) 2. Directed the Jira board from Iteration 2 on: wrote the Lab 3 and Iteration 2 user stories and entered them in Jira (PR #34), and proposed story ownership (PR #38) 3. Iteration 3: rewrote 7 stories and wrote 1 new one, each with business value and acceptance tests; set the points (32), owners and sprint 4. Acted on the Iteration 2 Jira feedback: closed the leftover Iteration 1 story, added the 3 missing Iteration 1 stories, marked cut features with the reason, and removed replaced stories 5. Made the scope calls: moved AI generation to Iteration 3 when it didn't fit in Iteration 2, and cut multiple choice | 1. Wrote the architecture contract in the Iteration 1 plan (app structure, data models, API error format) that the SDD describes (PR #6) 2. Edited the SDD for the Iteration 1 submission 3. Owned the SDD in Iterations 2 and 3: rewrote it to match what we built and added the diagrams the Iteration 1 grade asked for (architecture, backend classes, frontend modules, rating sequence) 4. Iteration 3: designed the AI generation architecture (Gemini behind a server-side provider with a stand-in for tests, the generations table, new error codes and limits), updated every diagram and added a card-generation sequence | 1. Edited the STD for the Iteration 1 submission 2. Iteration 2: checked the STD's test counts and coverage against CI, and recommended re-running the manual tests in the browser 3. Iteration 3: the documentation plan set out the STD's new test cases and live-site checks | 1. Presented in the Iteration 1 presentation 2. Recorded all demos, all iterations 3. Iteration 3: planned the presentation (one block per person, about 10 minutes) and the code walkthrough; presented security and the wrap-up; opened the code walkthrough; recorded the demo video on the live site | 1. Shared foundation: app factory, models, API skeleton and error format, dev setup (WS0, PR #7) 2. Backend auth: register, login, logout, current user (WS1, PR #8) 3. Request size limit with on-contract errors (PR #12) 4. Card scheduling fields and scheduler interface (PR #36), the spaced repetition scheduler based on Anki's defaults (PR #39), and saving a rating (PR #42) 5. Study API client and interval labels (PR #45), one design system for every page (PR #46), demo data with reset and time travel (PR #47), and the study card with rating buttons (PR #48) 6. AI generation backend foundation: migration, generations table, card origin, error codes, provider interface with a stand-in (0a, PR #60) 7. Generate page foundation: API client, route, page and AI badge (0b, PR #61) 8. Generate form with prompt, file upload and Suggest more modes (F1, PR #62) 9. Gemini provider and the flask ai-smoke check (B2, PR #64) 10. Refactor from our Iteration 2 feedback: one shared deck ownership check (PR #74) 29 merged PRs in all, including plans and releases | 1. Wrote tests with every PR from the plan's acceptance examples, e.g. auth (57 tests, PR #8) and the scheduler's exact intervals (PR #39) 2. Saving a rating, written test-first for Lab 3 (PR #42) 3. Set up frontend testing with Vitest and React Testing Library (PR #37) 4. Iteration 3: 0a's tests on SQLite and PostgreSQL (226 passing), 39 tests for the generate form, and the Gemini provider at 97% coverage, including checks that prompts and replies never reach the logs; ran live smoke tests against Gemini 5. Tested in review before requesting changes: a keyboard double-submit on the study page, with a failing test (PR #51), stale due counts (PR #56), a trailing-slash 404 in nginx (PR #63), 40 simultaneous accepts on PostgreSQL to prove the duplicate lock (PR #69), and every typed-answer example walked through in Chrome (PR #73) 6. Ran the test suites before approving a major pytest upgrade (PR #10) | 1. Dev setup in the shared foundation (PR #7), and the review of the Docker setup that got the containers starting (PR #3) 2. Fixed CI: pinned SQLAlchemy when 2.1 broke every PostgreSQL connection (PR #35), and made the frontend image always apply OS security updates after the image scan flagged OpenSSL (PR #44) 3. Iteration 3 deploy config: AI settings, docker-compose, .env.example, render.yaml, and nginx's upload limit and public backend address (0a, PR #60) 4. Set up the Gemini API key and chose the free-tier model, with billing never enabled (P1) 5. Opened the develop-to-main release PRs for Iterations 1 and 2 (PRs #32, #58), and managed commits and releases for all docs 6. Reviewed every Render deployment PR (#63, #68, #77–#84) | 1. Team Leader and Security Leader 2. Kept the project on track after losing two of our six members in Iteration 1, reassigning roles and re-scoping 3. Planned every iteration and assigned work by track and dependency, with shared foundations built first so teammates could work in parallel 4. Reviewed 32 of my teammates' 38 PRs, plus 5 Dependabot updates, and requested changes on 9, each with a reproduced problem and a suggested fix 5. Ran our meetings and day-to-day coordination on Discord; wrote the Iteration 1 meeting minutes and updated them in Iteration 2 6. Kept the READMEs and team page current, and managed each iteration's documents, release and submission | Security Leader work: request size limit (PR #12), password and email rules (PR #8), the Gemini key kept on the server and out of logs, billing never enabled, and daily generation caps. AI use (Claude, Claude Code, Zoom AI) is recorded in the AI Usage Log and in my AI usage appendices for each iteration.

## Miles Cameron
Your Lead Roles: Project Leader, Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/1-9/9 | 7 | 6 | 1 | 0 - learn about products related to our proposed project 5 - organize team meeting, keep group on target via discord, verify iteration requirements and team completion status 6 - set up project on local machine 7 - complete project documents | 0.5 |  |  |  |  | 2 | 0.5 | 3 | Used Claude to help do research and draft sections for the SPPP doc. Results helped speed the process and were good for brainstorming but required manual review for most portions. Used AI to sythesize secondary outputs such as readme file, glossary, and references sections | 1. Wrote 2 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation |  |  |  | 8
2026-02-03 | 9/10-9/23 | 27 | 25 | 2 |  | 2 | 1 | 1 | 6 | 1 | 6 | 3 | 5 | The Zoom transcript was too verbose and not tailored to the meeting minutes style, so I synthesized it before accepting. I used Claude to synthesize the meeting minutes into a more appropriate style, then edited the output to emphasize particular points. I used our SPPP document, written in plain English and laying out our full plans in detail, to have Claude create a technical implementation plan that could be shared with the whole team. I read through it, found it technically sound based on my experience, and submitted it as a PR for the team to review without modification. I asked Claude to use the Implementation 1 plan to draft Workstream 0 and posted the result as a PR without modification, knowing my teammates and I would review it as part of the PR process. I did the same for Workstream 1, again posting it as a PR without modification for team review. Claude provided briefings on all PRs, including the level of risk in accepting each, and I then decided whether to accept or provide feedback on each one. Finally, I used the state of our development after the weekend, prior course feedback, and our prior docs to have Claude suggest edits across all documents. I accepted some after my review because they showed good understanding and solid output; others missed the mark or were too verbose, so I edited them. | Completed the Iteration 1 implementation plan for our team: - Implemented two of the five work streams required for implementation. - Reviewed nearly every PR posted by teammates.- Kept the team on task through constant Discord communication. - Added supplemental PRs to polish off the iteration. - Got a live demo working. - Recorded the team's presentation. - Edited and committed every document due in this iteration. - Submitted the team's work for this iteration. | No real structural issues. Only issues related to starting an app from nothing and working to complete the assignments. | Continue to communicate thoroughly with teammates.Delegate more tasks to teammates to avoid late-night crunch upon submission.Continue breaking down implementation scope into plans. | Unclear. Pending team meeting to decide delegation and scope for next iteration | 20
2026-03-04 | 9/23-10/6 | 19 | 19 | 0 |  | 2 | 1 | 2 | 4 | 3 | 4 | 3 | 0 | Plan for finalizing iteration 2 — Read through the plan's breakdown of tasks and decided the scope was appropriate. Sent to the team for review, knowing the full team would read the plan. Plan step 0: foundation — Claude implemented code for step 0. I gave well scoped direction and then read through it. Given that this was purely foundational code and not functional, I felt comfortable submitting this as a PR for the team to review Plan step B1: demo data — Claude implemented demo data for iteration 1. Given that this was not functional code, but rather the seed for our demo, this was easy to accept, as I would find any issues with it later during the demo itself. Plan step F2 cards and rating buttons — Claude implemented step F2 relating to cards and rating buttons. I submitted this as a PR for the team to review, knowing the demo was close to being done and I could review any bugs manually at that point. Claude had also done an excellent job of implementation thus far due to the well-scoped nature of the inputs. PR Reviews — I had Claude boil down code changes to give me thorough reports and things to consider as I did a manual review. Documentation Updates — Claude reviewed our codebase compared to our past documentation freezes and recommended changes to each document to make our documentation reflect our latest codebase and decisions that I had used Claude for. | - Managed the Jira user story board for our team. - Created a plan for Lab 3 that had everyone writing code for iteration 2. - Edited the SDD. - Updated the meeting minutes. - Managed the iteration 2 submission PR. - Reviewed nearly every PR except my own. - Organized the team and assigned tasks at every stage. - Built the study card and rating buttons. - Built the seed data for the demo. - Completed the demo. - Built the app-wide style guide. - Built the study API client. - Built the spaced repetition scheduler. - Built the mechanism for saving a rating. | None | N/A | Implement AI card features and multi-answer/typed answer features. Submit iteration 3. | 20
6 | 10/7-10/13 | 22 | 21 | 1 |  | 0.5 | 1.5 | 2.5 | 5 | 2 | 7 | 0.5 | 2 | I used Claude Code for the Iteration 3 plan, my four implementation tasks (0a, 0b, B2, F1), a refactor from our Iteration 2 feedback, PR reviews, the Jira board, the SDD diagrams, and the documentation, presentation and code walkthrough plans. Claude implemented and tested each task, then stopped so I could review every file and make each commit and PR myself. It brought me only real decisions, in plain language, and I made each call, such as rejecting Gemini 3.8 Flash after it timed out. My Gemini key never went into the chat; I entered it and ran the live tests myself. In reviews, Claude proved its findings rather than asserting them: it ran 40 simultaneous accepts on PostgreSQL, rendered pages in a real browser, and walked every typed-answer example in Chrome. I decided what to post. When Claude Code's safety check blocked a merge and some Jira deletions, Claude handed them back to me instead of working around it. | 1. Wrote the Iteration 3 plan: architecture, contracts between tasks, owners and acceptance examples for every task (PR #59), and revised it after Duc's review 2. Built the backend foundation for AI generation (0a, PR #60) and the frontend foundation (0b, PR #61), so teammates could start their tasks the next day 3. Built the Gemini provider and flask ai-smoke (B2, PR #64) and the generate form (F1, PR #62) 4. Set up the Gemini API key and chose the model (P1) 5. Refactored the duplicated deck ownership check and added the missing AI-usage comments, from our Iteration 2 feedback (PR #74) 6. Reviewed 17 teammate PRs (#63, #65-#73, #77-#84) and requested changes on 4 7. Directed the Jira board: rewrote and assigned the Iteration 3 stories, cleaned up the board per the Iteration 2 feedback, and moved each story to Done as it shipped 8. Wrote the plans for the team's documentation updates, the presentation and the code walkthrough 9. Updated the SDD with five diagrams, the READMEs and the team page; managed commits and releases for all docs 10. Recorded the demo video on the live site, my presentation block and my code walkthrough segment 11. Managed the final release and submitted the team's work | 1. My first-choice Gemini model (3.8 Flash) timed out, and 3.5 Flash was sometimes overloaded on the free tier 2. Duc's plan review found the frontend couldn't reach the backend's private address on Render's free tier 3. GitHub showed a merge conflict on #73 that wasn't real, left over from earlier squash merges 4. Claude Code's safety check blocked merging #73 and deleting replaced Jira stories 5. Preparing the demo on the live site, I found each suggestion's Reject button was invisible | 1. Resolved: chose 3.5 Flash with Flash-Lite as the fallback; learners see a clear message when Google is busy 2. Resolved: the plan and 0a switched to the backend's public address 3. Resolved: merged the latest develop into the branch locally, with no file changes 4. Resolved: I merged #73 and ran the Jira deletions myself 5. Resolved: one-line style fix with a regression test, released before submission | None. Iteration 3 was the final iteration. | 0

## Duc Anh Nguyen
Your Lead Roles: DevOps Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/1-9/9 | 8 | 7 | 1 | 1 - define high level requirements 5 - make project plan (Infra and CI/CD) 7 - research similar products, infra plan, CI/CD tools, prepare presentation |  | 1 |  |  |  | 2 |  | 4 | Use ChatGPT to research similar product/platform like Anki. Also review CI/CD tools like Jenkins, ArgoCD and GitHub Actions, and use ChatGPT to refine the infra plan and elicitate some high level requirements, which we discussed in the team meeting. I validate and review the output and suggestions from AI and finalize plan with my decision and thinking. | 1. Write configuration management plan sections of SPPP 2. Set up branch and commit a test message on git and merge all member commits 3. Participate in Iteration 0 presentation 4. Presented presentation | 1. communication is not clear. Task assignments is not clear. | 1. communication preference and availability, establish expectations and team coordination as well as meeting practices | 1 - continue to define requirements 2 - Design the architecture of systems and review tech stacks 3 - Set up infra, build workflow and CI/CD | 8
2 | 9/10-9/16 | 12 | 11 | 1 | 1 - Analyze requirements with Jira tasks and sub tasks with user story 2 - Research system design and architecture 3 - Implementation of skeleton code for backend and frontend 6 - Set up docker and containerization and environment |  | 3 | 3 | 2 |  |  | 3 |  | Use Claude and Roku AI of Jira to plan the tasks and subtasks as well as set Docker and skeleton code for both backend and frontend | 1. Set up tasks and subtasks on Jira for ticket and project tracking 2. Set up skeleton code for backend and frontend 3. Set up Docker for containerization of the project | 1. Some issues with creating tasks with template on Jira and having difficulty for creating task with user story following the template |  | 1 - design the system 2 - Implement CI/CD 3 - Start implementing features 4 - improve github workflow | 16
3 | 9/17-9/23 | 18 | 16 | 2 | 2 - design system architecture 3 - implement CI/CD and auth frontend 6 - improve github workflows for development 7 - research AI workflows and architecture for AI features |  |  | 4 | 4 |  |  | 4 | 4 | Use Claude to help with the design of system architecture, review codes and implementation of frontend auth as well as CI/CD. Also improve the GitHub workflow for development and security | 1. Write system architecture SDD docs (all sections) 2. Write testing document STD (all sections) 3. Implement frontend for auth 4. Implement CI/CD 5. Set up and improve GitHub workflow for development 6. Review code | 1. Some issues with CI at first and some duplicate and time consuming tests, improve for faster CI 2. Some issues with branching and merge conflicts but resolved after that 3. Some bugs with frontend and were able to fixed and also improve some frontend logic of others | 1. Timeline still a bit tight and need more communication as well as more discussion in term of technical to help improve the project in general | 1 - research and design AI workflow for the AI generated features 2 - Set up infra, deployment platform for CD 3 - Improve system architecture and make it more scalable | 20
4 | 9/24-9/30 | 13 | 12 | 1 | 3 - implement study session reducer (Lab 3 Story 3) 4 - write tests first (red/green) for the session reducer 5 - review Lab 3 PRs (scheduler, card scheduling fields, Vitest setup, due cards, save rating) |  |  |  | 4 | 4 | 4 |  |  | Use Claude Code to write the session reducer test-first from the Lab 3 acceptance examples, and to review teammates' Lab 3 PRs. I verified the review findings myself, e.g. recomputed the scheduler arithmetic by hand, before posting. | 1. Implement study session reducer with tests (PR #40) 2. Review and approve Lab 3 PRs #33-#39, #41, #42 | 1. A new SQLAlchemy release (2.1) broke every PostgreSQL connection in CI 2. The scheduler PR (#39) had no red commit, which Lab 3 requires as evidence of test-first work | 1. Resolved: SQLAlchemy pinned to 2.0.54 (PR #35) 2. Raised in my review of #39; the PR was merged as one commit. My own reducer PR (#40) has a separate red commit | 1 - implement the study page (F1) and session summary (F3) 2 - add a frontend coverage report and gate to CI 3 - write tests for the untested Iteration 1 pages 4 - review Iteration 2 PRs | 20
5 | 10/1-10/6 | 19 | 18 | 1 | 3 - implement study page (F1) and session summary (F3) 4 - frontend tests for Iteration 1 pages and the study page 5 - review Iteration 2 PRs 6 - frontend coverage report and 90% gate in CI 7 - update SPPP and risk register for Iteration 2 |  |  |  | 4 | 4 | 4 | 4 | 2 | Use Claude Code to implement the study page and session summary from the acceptance examples, write frontend tests, add the coverage gate, review PRs, and update the SPPP and risk register with the Google Docs and Sheets connectors. I reviewed every change and corrected it where needed, e.g. direct edits instead of suggestions and the correct author. | 1. Implement study page F1 (PR #51) and session summary F3 (PR #49) 2. Add frontend coverage report and 90% gate to CI (PR #50) 3. Write tests for Iteration 1 pages, forms, auth and route guards (PR #52) 4. Review PRs #43-#48 and #54 5. Update SPPP and risk register for Iteration 2 | 1. Most Iteration 1 frontend pages had 0% test coverage when the coverage report was added 2. CI on develop failed because the image scan (Trivy) found OpenSSL vulnerabilities that a cached build layer skipped patching 3. Squash merges of #45 and #46 left stale commits on #48, so its diff showed 24 files 4. Deck ids change after flask seed --reset, so a walkthrough step passed without testing cross-user access 5. Render deploy hooks are still not configured, so CD skips deployment 6. Study mode and AI deck generation did not both fit in Iteration 2 with four members | 1. Resolved: tests for Iteration 1 pages, forms, auth and route guards (PR #52); frontend gate raised to 90% (174 tests, 91.66%) 2. Resolved: the frontend image always reruns its OS upgrade (PR #44) 3. Resolved: gave the rebase command on #48 and approved after the rebase 4. Resolved: the seed now prints each deck's id and the docs no longer assume ids 1 and 2 (PR #47) 5. Open: the demo runs on Docker Compose; configure the Render hooks in Iteration 3 6. Team finished study mode end to end and moved AI deck generation to Iteration 3 (Finalize Iteration 2 plan, PR #43) | 1 - AI deck generation: LLM service behind a server-side interface, validate model output before saving 2 - configure Render deploy hooks so CD deploys staging and production 3 - system-wide and regression testing, defect fixes 4 - release and final demo | 20
6 | 10/7-10/13 | 23 | 22 | 1 | 2 - review the Iteration 3 plan (contracts, Render free-tier limits) 3 - implement B1 prompt builder and cleanup, B3 generate endpoint, F2 review list; refactor shared frontend and API helpers 4 - tests for B1, B3 and F2 5 - review Iteration 3 PRs 6 - P2 Render setup: public API_ORIGIN, migrations in the start command, production database 7 - update CICD.md and the SPPP for Iteration 3 |  |  | 2 | 8 | 4 | 4 | 2 | 2 | Use Claude Code to implement B1, B3 and F2 from the plan's acceptance examples with tests, review teammates' Iteration 3 PRs, refactor shared helpers, set up Render, and update CICD.md and the SPPP with the Google Docs connector. I verified each review finding before posting, checked every number against CI, and removed narrative text and guessed values from the doc edits. | 1. B1 prompt builder and cleanup (PR #65) 2. B3 generate endpoint (PR #66) 3. F2 review list (PR #67) 4. P2 Render deployment: public API_ORIGIN (PR #63); Render Blueprint with the database, backend and frontend; deploy hooks and APP_URL in the production environment; migrations in the image's start command (PRs #68, #79, #81); database in the same region as the services (PRs #82, #83). Live at https://cadence-frontend-jufj.onrender.com 5. Shared frontend and API helpers refactor (PR #75) 6. Review PRs #59-#62, #64, #74, #76 7. Update doc/CICD.md and the SPPP for Iteration 3 | 1. Render's free tier has no pre-deploy command, so migrations could not run before a deploy 2. Render's free web services can't receive private-network traffic, so the frontend couldn't reach the backend at http://cadence-backend:5000 3. Gemini's free tier allows 20 requests a day for the whole project 4. In my review of PR #62, a file chosen earlier was still sent after switching modes 5. The production GitHub environment had no deploy hooks or APP_URL, so CD skipped deployment 6. Render passed the backend's start command from render.yaml to the shell with its quotes, so the backend exited with status 127 7. The database was created in Oregon while both services were in Ohio, so the backend couldn't resolve the database's internal hostname 8. PRs #77 and #78 were squash-merged, so main and develop no longer shared history and the next develop to main PR conflicted | 1. Resolved: migrations run as the backend starts 2. Resolved: API_ORIGIN is the backend's public address; CICD.md updated (PR #63) 3. Handled: generation is capped at 10 per user and 18 site-wide; tests use a stand-in provider 4. Resolved: fixed in PR #62 before I approved 5. Resolved: deploy hooks and APP_URL set; every green merge to main now deploys and checks /api/health 6. Resolved: the image's CMD runs the migration, then gunicorn (PRs #79, #81) 7. Resolved: all three pinned to Ohio in render.yaml and the database recreated there (PRs #82, #83) 8. Resolved: deployed from a branch with main merged in (PR #81); PRs into main now use a merge commit | 1 - P4 acceptance testing on the live site 2 - record my presentation block and code walkthrough segment 3 - approve the release PR 4 - add the story acceptance rate to the SPPP | 3

## Nurzat Mukhamedali
Your Lead Roles: Requirement Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/1-9/9 | 6.75 | 5.5 | 1.25 | 0 - learning about the projects with similar features and functionality 1 - developed high-level functional and non-functional requirements 6 - Set ip and practiced Git/GitHub workflow 6 - completed Lab 1 | 0.5 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | I used ChatGPT to learn more about Git and GitHub functionality. Also, I used it to troubleshoot some problems that occurred during the process. | 1. Proposed High-Level requirements as a Requirement Leader, including essential, desirable, optional, and nonfunctional requirements 2. Completed Lab 1 Git/GitHub contribution and updated team.md. | 1. Encountered a couple of problems with GitHub such as merge conflict and aunthentication issues when pushing through Terminal 2. Still learning about Github 3. Working with Google Drive and GitHub, communicating through Discord, completing tasks on Blackboard is a bit overwhelming | 1. Resolved the merge conflict and authentication issues 2. Continue learning about Git and GitHub through labs, upcoming project works, and self-study 3. Improve organization by regularly checking each platform and staying on track of all the tasks and deadlines | 0 - continue to learn Git/GitHub 1 - Complete Lab 2 and Quiz 1 1 - Continue requirement analysis and management as Requirement Leader by working further on user stories 2 - learn more about the transition from requirements to design | 8
2 | 9/10-9/16 | 8 | 7.5 | 0.5 | 0 - Studied course material and completed Quiz 1. 6 - Completed Lab 2 and practiced the development tools and workflow. | 4.5 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | I used ChatGPT to prepare for Quiz 1 by reviewing course concepts and clarifying topics I did not understand. I also used it for help understanding and completing Lab 2. The explanations helped me work through the material and the lab tasks. | Completed Quiz 1 and Lab 2 as individual coursework. | Still building confidence with development tools and the Git/GitHub workflow. | Continue practicing through project work and ask teammates for clarification when needed. | 0 - Learn the frontend concepts needed for Iteration 1. 1 - Clarify requirements for deck and flashcard management. 2/3 - Design and implement the deck and card interface. 4 - Test the main user workflows. 5 - Coordinate integration and prepare the Iteration 1 presentation. | 10
3 | 9/17-9/23 | 16 | 15 | 1 | 0 - Learned frontend development basics, npm, and the pull request review process. 1 - Clarified the deck and card workflow, including empty states, creating the first card, and Finish/Cancel behavior. 2 - Refined the layout and interactions for deck and card management. 3 - Implemented the WS4 frontend for creating, editing, and deleting decks and cards; addressed review feedback and the expired-session issue. 4 - Checked user workflows and regression fixes, and participated in reviewing teammates’ pull requests. 5 - Coordinated with teammates on integration and prepared Iteration 1 presentation slides and narration. 6 - Set up frontend dependencies and resolved branch integration conflicts. | 2 | 1 | 1.5 | 5 | 2 | 2 | 1.5 | 0 | Used Codex and ChatGPT to understand frontend development and Git/GitHub, assist with implementation and testing, investigate review feedback, and prepare presentation material. AI helped generate code, explain errors, and suggest fixes. I checked the interface in the browser, reviewed the explanations and test results, and incorporated teammate feedback through the pull request process. | Contributed the WS4 deck and card frontend through PR #16, including deck/card management, input validation, empty states, and improved card creation and cancellation flows. Addressed integration conflicts and review feedback, including expired-session handling. Helped prepare the group’s Iteration 1 presentation and prepared narration for slides 2, 4, 7, and 10. | Limited prior frontend development experience required additional learning. Integration with teammates’ authentication and routing changes caused merge conflicts. Review feedback identified an expired-session issue that needed correction. | Resolved the integration conflicts and implemented the expired-session fix. Incorporated review feedback and checked the updated workflows. Continue improving familiarity with the codebase and coordinate with teammates on the next iteration. | 1 - Review Iteration 1 feedback and refine requirements for Iteration 2. 1/2 - Clarify the planned study workflow and spaced repetition behavior with the team. 4 - Continue checking existing features and address any reported issues. 0 - Continue learning React and frontend testing. 5 - Coordinate priorities and responsibilities with teammates. | 8
4 | 9/24 - 9/30 | 11 | 11 | 0 | 0 – Reviewed course material and completed Quiz 2; learned about TDD and automated testing. 1 – Reviewed the Lab 3 Story 2 requirements and acceptance criteria for retrieving due cards. 3 – Completed the due-cards endpoint implementation for Lab 3. 4 – Completed the RED and GREEN testing phases; verified all 11 Story 2 tests passed locally and inside Docker; captured the required screenshots. 6 – Used Git branches and Docker CLI commands to develop and verify the lab work. | 3 | 1 | 0 | 2.5 | 3 | 0 | 1.5 | 0 | Used OpenAI Codex to understand the Lab 3 requirements, create pytest tests, implement the due-cards endpoint, and run tests locally and inside Docker. I directed the work in separate RED and GREEN phases and captured screenshots of the failing and passing results. AI explanations helped me understand TDD, test fixtures, and Docker test commands. | Completed Lab 3 Story 2: Due Cards, including the backend endpoint, 11 automated tests, and screenshots documenting the RED, GREEN, and Docker test results. Completed Quiz 2 as individual coursework. | Docker Desktop’s GUI did not open, although Docker was running from Terminal. Needed additional guidance on the TDD process and running tests inside the container. | Completed Docker verification through the CLI. All 11 Story 2 tests passed inside the container. Continue building familiarity with backend testing and Docker commands. | 1 – Review Iteration 2 requirements and acceptance criteria. 3 – Implement B2 due counts and F4 deck-page updates. 4 – Test the new features and address review feedback. 5 – Prepare the Iteration 2 presentation and coordinate with teammates. | 10
5 | 10/01 - 10/07 | 15 | 15 | 0 | 1 – Reviewed the Iteration 2 plan and clarified B2/F4 requirements and expected behavior. 3 – Completed B2: added due counts to deck API responses. Completed F4: added Study buttons, due-count badges, and card schedule badges. 4 – Verified automated tests and CI results; addressed review feedback about refreshing due counts after adding or deleting cards. 5 – Created the Iteration 2 PowerPoint using Miles’s updates, prepared and shortened the speaking script, and recorded the presentation. Miles provided the recorded demo segment. | 0 | 1 | 0 | 6 | 3 | 5 | 0 | 0 | Used Devin to implement B2 and F4 with automated tests and to address review feedback. I applied the provided patches and checked the results against the team’s acceptance criteria. Used OpenAI Codex to prepare the PowerPoint and speaking script from Miles’s updates, explain technical concepts, and shorten the narration. I revised the script for a single presenter with Miles’s recorded demo. | Delivered B2 through PR #55 and F4 through PR #56. These changes display available study counts and card schedules and let users start studying from the deck pages. Created the Iteration 2 presentation slides and recorded the narration. Contributed to the team’s completed Iteration 2 delivery. | Review identified that due-count badges did not refresh after adding or deleting a card. The presentation script also needed shortening to avoid repeating material already covered in Iteration 1. | Updated the deck page to refresh due counts after card changes and added regression tests. Both PRs merged with passing CI. Shortened slides 4-8 and adapted the presentation for my narration and Miles’s recorded demo. | 1 – Review Iteration 2 feedback and clarify Iteration 3 requirements, including AI card generation and review before saving. 4 – Continue regression testing and address reported issues. 5 – Coordinate Iteration 3 responsibilities and update the progress and AI usage logs. | 10
6 | 10/08 - 10/14 | 12 | 11.5 | 0.5 | 0 – Completed the weekly quiz. 3 – Implemented the typed-answer checker, typed-mode building blocks, and typed study flow for Iteration 3 through PRs #71–73. 4 – Tested typed-answer functionality and verified passing CI checks for all three approved PRs. 5 – Prepared the Iteration 3 presentation slides and speaker notes, recorded my presentation and code walkthrough segments, and edited the team’s presentation recordings into one video. Updated meeting minutes and my progress report. | 1.5 | 0 | 0 | 6 | 1 | 3 | 0 | 0 | Used Devin to help prepare and organize the typed-mode code into PRs #71–73. Used OpenAI Codex to draft presentation slides and speaker notes, organize project responsibilities, and prepare progress-report wording. The three PRs received approval and passed CI. | Contributed Iteration 3 typed-answer functionality through PRs #71–73. Prepared presentation materials, recorded my presentation and code walkthrough sections, assembled the team’s presentation video, and updated meeting documentation and my progress report. | Finalizing shared presentation content and collecting individual recordings required coordination with teammates. | Coordinated with teammates to align the presentation content, collect recordings, and complete the final presentation materials. | 0 – Review course material and take the online final exam during October 14–17. Iteration 3 is the final project iteration, so no additional development work is planned. | 10 hours (8 hours for review, 2 hours for exam)

## Osasenaga Okunbor
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 9/17-9/23 | 8 | 7 | 1 | 3 - implement deck and card endpoints 4 - write tests for the endpoints 5 - respond to code review, fix review comments, update the team 6 - set up local environment and run tests |  |  |  | 2 | 2 | 1.5 | 1.5 |  | Used Claude to help draft the deck and card endpoints and tests, and to guide me through git, the pull request, and fixing review feedback. Helpful for speed and for learning the workflow. The code needed checking: CodeQL flagged issues and a reviewer found two weak test assertions. I ran the full test suite (94 passing) locally, fixed both, and pushed. | 1. WS2 backend: deck and card endpoints (GET/POST/PATCH/DELETE) with 36 new tests, PR #17 merged into develop. 2. Fixed CodeQL alerts and code review comments. 3. Added my signature to the SPPP. | 1. Docker wasn't running, so I ran tests locally without it. 2. First push failed CodeQL, and code review found two weak test assertions. | Tests pass locally and in GitHub checks. 2. Both fixed, checks green, PR approved and merged. | 1- test the deck and card flow end to end once the frontend is connected 2 - support Duc and Nurzat as they connect to the endpoints | 8
3 | 9/24-9/30 | 10 | 10 | 1 | 3 - add duplicate-card rule to create_card 4 - TDD: failing test first, then the fix, run locally and in Docker | 1.5 | 2.5 |  |  |  | 4 | 4 |  | Used Claude to draft the failing test and the fix. I ran the tests myself at each step, locally and in Docker. | 1. Lab 3: duplicate card rule built with TDD (red: 1 failed / 94 passed, green: 95 passed, also in Docker) | Was sick for part of the week | 1. B3 is finished and up for review (PR #53). Next iteration I'll post a short update on Discord as soon as I'm behind, so the team can plan around it 2. Learned to use git stash to save unfinished work before switching branches, and to start each task from an up-to-date develop 3. Wrote tests straight from the reference table, so any wrong number fails CI before it reaches the frontend | 1 - fix any review comments on PR #53 2 - help test the Iteration 2 walkthrough | 6
5 | 10/1-10/7 | 8 | 8 | 1 | 3 - B3 interval previews (PR #53) 4 - tests from the plan's reference table; updated the STD with actual results for all 13 manual tests 5 - progress report, AI log, team updates |  |  |  | 3 | 4 | 1 |  |  | Used Claude to draft B3 and its tests, and to update the STD. I ran the tests in Docker (185 passing), checked the values against the plan, and checked each STD result against the run. | 1. B3 interval previews, PR #53, merged 2. STD updated for Iteration 2 (actual outputs, defects row, metrics) | 1. Sick most of the week, so I started late | 1. B3 merged on 10/4. To avoid falling behind again, I'll start each task as soon as it's assigned and post on Discord if I'm stuc | 1 - B4 accept and reject endpoints 2 - F3 Generate with AI button and AI badges 3 - STD and risk management docs | 10
6 | 10/8-10/14 | 9 | 8 | 1 | 3 - B4 accept/reject endpoints (PR #69); F3 Generate with AI button and AI badges (PR #70) 4 - wrote tests first for both and ran the full suites 7 - STD and risk management docs |  |  |  | 4 | 3 |  |  | 1 | Used Claude to write B4 and F3 test-first from the Iteration 3 plan. I checked the tests failed first, ran the full suites (391 backend, 266 frontend), and reviewed both PRs before opening them. | 1. B4 accept and reject endpoints, PR #69 2. F3 Generate with AI button and AI badges, PR #70 3. STD and risk management sheet for Iteration 3 | 1. Started late, so both PRs went up right at code freeze | 1. Both PRs are up with all tests passing and are waiting for review. Next time I'll open a draft PR early so the team can see progress | 1 - fix any review comments on PR #69 and #70 2 - add the STD's live-check results after the release | 6